## Slide 1: Business
2021

## Slide 2: FAQ’s
Can you choose both Business and Economics?
Do you need to have studied Business at GCSE?
How is work divided between BGS and BHS?
BHS (Theme 1 and 3) BGS (Theme 2 and 4)
YES
NO

## Slide 3: What do we study?
Functional areas of a Business
  Accounting and finance
  Human resources
  Operations management
  Marketing
  External environment

## Slide 5: Business decisions and strategy
  Detailed research and planning:
    Are important when undertaking an event
    Reduces the risk of things going wrong

## Slide 6: Making strategic decisions
This topic covers the various techniques that may be used by the business to inform their strategic decision making.
Students should consider non-financial information as well information generated by the techniques to aid decision making

## Slide 8: Critical Path Analysis

## Slide 9: Get a pencil and paper
Write down all of the steps involved in order to brew a pot of tea and serve one cup of tea!
Estimate the duration of each task!
How long will it take for you to make one cup of tea?
Am I missing something?
Does it really take this long?
Open up record sheet

## Slide 10
Activity | Description | Seconds
A | Fill kettle, connect to mains | 
B | Boil kettle | 
C | Put tea in pot | 
D | Pour boiling water in to pot and brew | 
E | Prepare cups and saucers | 
F | Pour milk in to cup | 
G | Put sugar in to cup | 
H | Pour brewed tea in to cup | 
I | serve | 
 | Total time taken | 

## Slide 11: Timings
Activity | Description | Seconds
A | Fill kettle, connect to mains | 15
B | Boil kettle | 90
C | Put tea in pot | 10
D | Pour boiling water in to pot and brew | 130
E | Prepare cups and saucers | 20
F | Pour milk in to cup | 10
G | Put sugar in to cup | 10
H | Pour brewed tea in to cup | 10
I | serve | 5
 |  | 300
 |  | 5 minutes

## Slide 12: Construct your networks!
Identify the order of each activity.
Now determine which activities follow on from a previous activity (Boil kettle follows on after filling kettle with water)

## Slide 13
Label each activity correctly

## Slide 14: Critical Path
A
15
B
90
C
10
D
130
E
20
F
10
G
10
I
5
H
10
How long will it take?
Why have I highlighted A,B,D.H.I in red?
Which activities must be closely supervised?
250 seconds

## Slide 15: Boston Matrix